## Sheet1
PalMTouchStone Project Cost Estimate
Prepared by: Gopi Amara | Date: | 2019-06-03
| Units/Hrs. | Cost/Unit/Hrs. | Subtotals | WBS Level 2 totals | % of totals
WBS Items
1.Sketching |  |  |  | 3675 | 15.26%
1.1 Project Manager | 30 | 30 | 900
1.2 Team Lead | 35 | 45 | 1575
1.3 UI Designer and UI Developer | 30 | 40 | 1200
2.Sample Data |  |  |  | 1800 | 7.47%
2.1 Developer | 40 | 45 | 1800
3.Architecture |  |  |  | 4090 | 16.98%
3.1 Project Manager | 45 | 40 | 1800
3.2 MVP Tools | 1 | 40 | 40
3.3 MVP Developer | 50 | 45 | 2250
4.Development |  |  |  | 5170 | 21.47%
4.1 MS Office licenses | 2 | 20 | 40
4.2 Project Manager | 35 | 50 | 1750
4.3 Team Lead | 40 | 35 | 1400
4.4 Developer | 40 | 50 | 2000
4.5 Project management tools | 1 | 20 | 20
5.Testing |  |  |  | 9350 | 38.82%
5.1 Test Manager | 30 | 45 | 1350
5.2 Test Lead | 40 | 50 | 2000
5.3 Project Team members | 120 | 50 | 6000
Total Project Cost Estimates |  |  |  | 24085 | 100%