## Sheet1
PuMpUp Project Cost Estimate
| Units/Hrs. | Cost/Unit/Hrs. | Subtotals | WBS Level 2 totals | % of totals
WBS Items
1.Project Management |  |  |  | 192800 | 59.52%
1.1 Project Manager | 120 | 200 | 24000
1.2 Team Lead | 110 | 180 | 19800
1.3 Software Developer & DB administrator | 800 | 160 | 128000
1.4 HR and testing | 150 | 140 | 21000
2.Hardware |  |  |  | 12000 | 3.704%
2.1 Mobile Devices | 5 | 400 | 2000
2.2 Laptops | 5 | 1200 | 6000
2.3 Desktop | 5 | 800 | 4000
3.Software |  |  |  | 4600 | 1.42%
3.1 MS Office licenses | 6 | 150 | 900
3.2 Windows Operating System | 5 | 150 | 750
3.3 Cloud Database | 20 | 25 | 500
3.4 Project management tools | 15 | 30 | 450
3.5 Server | 5 | 400 | 2000
4.Testing (25% of total project cost) |  |  |  | 60000 | 18.52%
5.Training and support |  |  |  | 18350 | 5.664%
5.1 Trainee cost | 100 | 105 | 10500
5.2 Travel cost | 50 | 150 | 7500
5.3 Project Team members | 5 | 70 | 350
6. Recruiting |  |  |  | 28200 | 8.705%
5.1 Travel cost | 40 | 500 | 20000
5.2 Lodging | 40 | 100 | 4000
5.3 Equipments | 60 | 70 | 4200
6.Reserves |  |  |  | 8000 | 2.47%
Total Project Cost Estimates |  |  |  | 323950 | 100%