## Sheet1
Risk Register for PalMTouchStone Project
No. | Rank | Risk | Description | Category | Root Cause | Potential Responses | Impact
1 | 1 | Budget Overflow | There can be increase in the budget amount due to sudden increase in price of resources | Financial Risk | Sudden increase in price of resources | Risk Acceptance | High
2 | 4 | Similar kind of product existing in market | Due to lack of knowledge of products in market, we tend to build similar existing product | Market Risk | Lack of knowledge of market products | Risk Mitigation | Medium
3 | 5 | Employees may leave the company | If we impose unacheivable deadlines, employees may feel hectic and leave the company | People Risk | Hectic schedule in order to complete the project | Risk Mitigation | Medium
4 | 3 | New technology availablility during project development | If there is no proper forecast of the upcoming technologies, we used the present technologies which may need to be replaced. | Technology Risk | In proper forecasting | Risk Transference | Medium
5 | 2 | Recession in market | Demand for the product had reduced due to an inflation in the country’s economy | Market Risk | Inflation | Risk Acceptance | High
6 | 6 | Lack of diversity of employees | If all the employees are from same location, then all of them will take leave incase of any disaster in their location | People Risk | Improper recruitement | Risk Avoidance | Low
7 | 7 | Natural Disasters | If there is no contingent planning to confront climatic disasters then there may be property loss and sudden increase in expenditure. | Financial Risk | Improper planning to confront it | Risk Acceptance | High